## PERMITTEE Full Action Plan
PERMITTEE
Associated Brochures and other hand-outs
Measure/Topic | Minimum Measure (in order of app) | Priority if Applicable | Activity - BMP | Responsbile Entity (if committed to in PEP) | Frequency | Evaluation Mechanism/Measure of Usage of Facilities or Material | Comments - activity | Complete
Public Participation | 1 |  | Post SWMP and Progress Reports to the community website. Include a link on the community website to the GLRC website. Follow the local public notice requirements. | Permittees | Continously. Update SWMP and Progress Report links to keep current. | Track website traffic
Develop and Maintain Master PEP | 2 |  | Update the PEP based on BMPs completed as part of community specific programs and procedures. | Permittees | Update BMPs completed with progress report. 1st and 4th year of permit.
PEP Evaluation and Effectiveness | 2 |  | Partner with the GLRC to conduct another follow up survey to determine PEP effectiveness . | Permittees | Once per permit cycle | Survey completed at end of permit cycle.
PEP A: Public Responsibility & Watershed Stewardship | 2 | M | Continue to maintain watershed signage. | Permittees | Replace as needed | Number of signs, maintenance activities.
PEP A: Public Responsibility & Watershed Stewardship | 2 | M | Promote "do you know your watershed" brochure, or related materials to general watershed education through events, lobby, and website | Permittees | Continously in lobby. during events | Number of brochures/materials provided to the public, web site traffic | Corresponding topic area: B |  | "Do You Know Your Watershed" Tri-fold, bracelets, stickers, etc.
PEP A: Public Responsibility & Watershed Stewardship | 2 | M | Display GLRC educational display in lobby and/or community events. | Permittees | Displayed in lobby or public location at least once annually for 2-3 weeks | Display utilized annually | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | M | Promote and distribute news article series developed for PEP topic areas on website/local newsletters/community news papers (as indicated in PEP) | Permittees | Continuously available online. Distribute in community newsletter if committed, as frequently as committed in PEP | Number of articles distributed, track website traffic | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP B: MS4 Connection | 2 | H | Distribute quarterly newsletter and annual report to public via community website, lobbies, and provide to administration. | Permittees | Quarterly/Annually | Number of people reached, track website traffic, copies distributed | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP C: Reporting Illicit Discharges | 2 | H | Provide contact information for reporting illicit discharges and illegal dumping on website. | Permittees | Continuously | Website traffic
PEP D: Car Washing | 2 | M | Promote the poster/brochure series (or similar content) on: car washing, motor oil, fertilizer, pet waste. Provide at community events , website and lobbies | Permittees | Continously | Track number of materials provided to public, website traffic, | Corresponding topic areas: A, B, F, G |  | PEP D: Handouts
PEP E: Disposal of Pesticides | 2 | M | Coordinate with Topic Area G
PEP F: Disposal of Pet Waste, etc. | 2 | M | Post materials related to leaf litter disposal and grass clippings to website, provide at community events. | Permittees | Continuously | Track number of materials provided to the public, website traffic | Corresponding topic area: A |  | PEP F: Handouts
PEP F: Disposal of Pet Waste, etc. | 2 | M | Continue to maintain pet waste signage at local parks, dog parks, trails, etc. | Permittees | Continuously | Track number of signs posted, maintenance activities | Corresponding topic areas: A, D
PEP G: P2 HHW | 2 | M | Promote local household hazardous waste, local travel trailer waste stations, yard waste procedures and recycling events via email and website postings | Permittees | Seasonally | Website Traffic | Corresponding topic areas: D, E
PEP H: Septic System Care | 2 | L | Coordinate with Topic Area A/Post links to local County programs related to septic inspections (Ingham Counties). Promote proper septic system care on website. | Permittees | Continuously | Website traffic | Corresponding topic area: A
PEP I: GI & LID | 2 | H | Promote LID/GSI brochure, post on website, lobby, etc. | Permittees | Continuously | Track number of materials provided to the public and website traffic | Corresponding topic area: A |  | Green Infrastructure Trifold Brochure, Rain Garden Seed Card
PEP I: GI & LID | 2 | H | Promote local projects on website, public meetings, etc. Share with GLRC Crd for inclusion on MyWatersheds.org | Permittees | Continuously | Track website traffic, number of projects posted | Corresponding topic area: A
PEP I: GI & LID | 2 | H | Send appropriate staff/elected officials to GLRC seminars. | Permittees | 2 per permit cycle | Track number of participants | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | M | If you have an industrial pre-treatment program, describe your connection with local businesses, industries here. The IPTP can help you connect and ultimately educate them. | Permittees |  | Number of business reached, etc. | Corresponding topic area: A
IDEP | 3 |  | Implement the municipal separate storm sewer system Illicit Discharge Elimination Plans (IDEP). Include nested jurisdictions if applicable. | Permittees | Continuously | Number of corrective actions taken
IDEP - mapping/locations | 3 |  | Maintain the GPS (Lat/long) locations of all MS4 outlets to waters of the state (optional) | Permittees | Maintain
IDEP - maintaining mapping system | 3 |  | Maintain the location of an up-to-date storm sewer map(s) (part of the IDEP). | Permittees | Maintain
IDEP - prioritize the system | 3 |  | Implement the procedure for prioritizing the identification and investigation of outfalls and points of discharge (part of the IDEP). | Permittees | Continuously | Procedure implemented
IDEP - prioritize the system | 3 |  | Maintain the geographical location of each prioritized area using either a narrative description or a map detailing the prioritized area (part of the IDEP). | Permittees | Maintain | Maintain prioritized area location
IDEP - screening | 3 |  | Implement the procedure and schedule for conducting field observations at all of outfalls and point of discharge in priority areas (part of IDEP). | Permittees | Complete by end of permit cycle | Number of outfalls and points of discharge observed
IDEP - screening | 3 |  | Perform field observations at points of discharge, once per permit cycle in the prioritized area or entire MS4. | Permittees | Complete by end of permit cycle | Number of outfalls and points of discharge observed
IDEP - screening | 3 |  | Implement the procedure for performing field screening if flow is observed and a potential source is not identified (part of IDEP). | Permittees | As identified | Number of field screenings performed
IDEP - Source investigation | 3 |  | Implement the procedure for performing a source investigation if the source of an illicit discharge is not identified by field screening (part of IDEP). | Permittees | As identified | Number of source investigations performed.
IDEP - response | 3 |  | Implement the procedure for responding to illegal dumping/spills (part of IDEP). | Permittees | As identified | Number of spills/illegal dumping responded to
IDEP - response | 3 |  | Implement the procedure for responding to illicit discharges outside the priority areas. | Permittees | As identified | Number of illicit discharges reported and responded to outside the priority areas
IDEP - reporting | 3 |  | Implement the procedure for reporting any release of any polluting materials from the MS4 to waters of the state as identified by the Part 5 Rules (part of IDEP). | Permittees | As identified | Number of incidents reported
IDEP - training | 3 |  | Train new employees within the first year of employment and other staff once during the permit cycle on all procedures described in the IDEP. | Permittees | Once per permit cycle or first year of new hire | Number of staff trained
IDEP - evaluation | 3 |  | Implement the procedure for evaluating overall effectiveness of the IDEP. Review guidance documents. | Permittee | Annually | Review performed.
IDEP - regulatory authority | 3 |  | Implement the IDEP ordinance or other regulatory mechanism that satisfies the IDEP section of the permit. | Permittees | Continuously | Number of illicit discharges eliminated, timeframe for eliminating the discharge, enforcement actions taken.
Construction SW | 4 |  | Implement the procedure for notifying the Part 91 agency or appropriate staff when soil or sediment is discharged to the MS4. | Permittee | Continuously | Number of notifications
Construction SW | 4 |  | Implement the procedure for notifying the MDEQ when soil, sediment, or other pollutants are discharged to the MS4 | Permittee | Continuously | Number of notifications
Construction SW | 4 |  | Implement the procedure for ensuring that construction activity one acre or more obtains a Part 91 permit or is conducted by an approved Authorized Public Agency as appropriate. | Permittee | Continuously | % of Part 91 permits obtained as part of site plan review. Number of projects conducted as an APA.
Construction SW | 4 |  | Implement the procedure for advising the landowner or recorded easement holder of the State of Michigan Permit by Rule. | Permittee | Continuously | % of landowner or recorded easement holders notified of Permit by Rule as part of construction activity.
PCSWC - regulatory authority/design criteria | 5 |  | Implement an ordinance or other regulatory mechanism that covers the water quality treatment performance standard and channel protection performance standard as described in section VII. The ordinance or regulatory mechanism should cover questions in the PCSWM portion of the permit. | Permittees | Continuously | Number of ordinances/regulatory mechanisms adopted
PCSWC - alternative approach | 5 |  | If utilizing the alternative approach, or off-site mitigation or payment in lieu programs, implement the procedure (included in PCSWC manuals). | Permittees | Continuously | Number of alternative approaches adopted
P2 Good Housekeeping - implementation | 6 |  | Implement site-specific BMPs/SOPs for each facility, operation and structure. Use the P2/good housekeeping manuals for scheduling and inspection criteria. | Permittees | Continuously | Number of SOPs/BMPs adopted, facilities included, etc.
P2 Good Housekeeping - implementation | 6 |  | Implement employee training schedule. New employees shall be trained within the first year of employment, other staff once during the permit cycle. | Permittees | Once per permit cycle or first year for new hire | Number of staff trained
Not required to be in SWMP (should already be in place/done as a pre-application process)

## COORDINATOR Full Action Plan
COORDINATOR
Measure/Topic | Minimum Measure (in order of app) | Priority if Applicable | Activity - BMP | Responsbile Entity | Frequency | Evaluation Mechanism/Measure of Usage of Facilities or Material | Comments - activity | Complete
Public Participation | 1 |  | Post master PEP, Progress Report template, etc. to the GLRC website. | GLRC Crd | Continuously | Track website traffic related to the documents
PEP: Website Management and Education | 2 |  | Update the www.mywatersheds.org website and social media outlets with watershed wide educational material, permit information and meeting information for the various committees of the GLRC. Include links to all community websites. | GLRC Crd | Continuously | Website traffic, social media analytics
PEP Collaboration | 2 |  | Continue to represent the GLRC on a regional public education campaigns with the Middle Grand River Organization of Watersheds (MGROW). | GLRC Crd | Continuously | Effectiveness of educational materials/strategies provided by MGROW | .
PEP A: Public Responsibility & Watershed Stewardship | 2 | M | Promote "do you know your watershed" brochure, or related materials to general watershed education through website, social media, etc., update as appropriate. | GLRC Crd | Update as needed. Materials will be distributed at events, annually at Adopt A River, QWS, MWEA Watershed Summit, etc. | Number of brochures/materials provided to the public. Web traffic and social media analytics. | Corresponding topic area: B
PEP A: Public Responsibility & Watershed Stewardship | 2 | M | Promote Mid-MEAC's volunteer stream monitoring effort through website and social media | GLRC Crd | Fall and Spring of Each Year (if event is held) | Potential volunteers reached through website and social media | Corresponding topic areas: C, J
PEP A: Public Responsibility & Watershed Stewardship | 2 |  | Display GLRC educational display at annual events (ex. Adopt A River/Quiet water,etc) | GLRC Crd | Multiple times annually | Number of events the display is used for | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | M | Promote and distribute news article series developed for PEP topic areas through email distribution, website, and social media | GLRC Crd | Monthly social media post of article or related content. Continously on website. with quarterly newsletter | Number of articles on website, email distribution, web traffic, social media analytics | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP B: MS4 Connection | 2 | H | Maintain and update the GLRC webpage. Sections "Stormwater Basics" and "What's a Watershed?" promote watershed health information and steps citizens can take. Update as appropriate. | GLRC Crd | Continuously | Track website traffic on page, social media analytics | Corresponding topic area: A
PEP B: MS4 Connection | 2 | H | Quarterly newsletters and annual report developed & distributed through email list, social media and website. | GLRC Crd | Quarterly/Annually | Number of people reached via email, track website traffic, social media | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP C: Reporting Illicit Discharges | 2 | H | Maintain the GLRC webpage, social media that lists contact information for all members and the state hotline regarding reporting of illicit discharges and illegal dumping. | GLRC Crd | Continuously | Track website traffic on IDEP section. |  | Y
PEP D: Car Washing | 2 | M | Promote the poster/brochure series (or similar content) on: car washing, motor oil, fertilizer, pet waste. Provide at community events and post to website and social media | GLRC Crd | Continuously | Track number of materials provided to public, website traffic, and social media analytics | Corresponding topic areas: A, B, F, G
PEP G: P2 HHW | 2 | M | Promote local household hazardous waste and recycling events via email and website postings, social media. | GLRC Crd | Continuously | Website traffic and social media analytics, newletters distribution. | Corresponding topic areas: D, E | Y
PEP H: Septic System Care | 2 | L | Coordinate with Topic Area A/Post links to local County programs related to septic inspections (Ingham County). Promote proper septic system care and 319 partner materials, etc. on GLRC website, social media. | GLRC Crd | Continuously | Website traffic, social media analytics | Corresponding topic area: A | Y
PEP I: GI & LID | 2 | H | Promote LID/GSI brochure, post on website, social media, and use with educational display | GLRC Crd | Continuously | Track number of materials provided to the public, website traffic, social media analytics. | Corresponding topic area: A
PEP I: GI & LID | 2 | H | Maintain and update the GLRC webpage listing local LID projects. | GLRC Crd | Continuously | Track website traffic and number of projects posted. | Corresponding topic area: A
PEP I: GI & LID | 2 | H | Organize seminars/events that GSI and GSI best management practices. Promote through email, websites, social media. | GLRC Crd | 2 per permit cycle | Track number of participants and number of events | Corresponding topic area: A
PEP I: GI & LID | 2 | H | Promote Greening Mid-Michigan on website | GLRC Crd | Continuously | Website traffic/video views | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | M | Educate business community on MS4 pollution prevention. Share information on how operations impact MS4 and how businesses can help educate costumers | PEP Committee | Twice per permit cycle | Number of businesses reached, etc. | Corresponding topic area: A
IDEP - training | 3 | 1 | Track the usage of the Excal Visual employee training video "Illicit Discharge Detection and Elimination: A Grate Concern". | GLRC Crd | Continuously | Collective number of staff trained
IDEP - training | 3 | 2 | Provide a training session showing the training video for all GLRC members twice during the permit cycle. | GLRC Crd | 2 sessions per permit cycle | Number of staff trained
IDEP - training | 3 | 3 | Coordinate with the City of Lansing IDEP training program when appropriate. | GLRC Crd | Continuously | Collective number of staff trained
P2 Good Housekeeping - employee training | 6 | 1 | Maintain and track the usage of the Excal Visual employee training videos "Rain Check" and "Storm Watch". Both are for MS4 good housekeeping programs. | GLRC Crd | Continuously | Number of staff trained
P2 Good Housekeeping - employee training | 6 | 2 | Provide a training session showing the training video for all GLRC members twice during the permit cycle. | GLRC Crd | Twice per permit cycle | Number of staff trained
TMDL Implementation - water quality data | 7 | 1 | Maintain the Master Water Quality Database to assist GLRC members with potential monitoring programs related to the TMDL. Data includes all local sources of monitoring from biological to chemical, pathogens, etc. | GLRC Crd | Continuously | Amount of monitoring data, number of active monitoring programs
Progress Reports | 8 | 1 | Provide updated progress report templates and other applicable materials to GLRC members for preparation of individual progress report submittals. | GLRC Crd | Continuously | Track all GLRC activities listed in action plan and other related documents. Evaluate collective efforts as part of progress report submission

## COMMITTEE Full Action Plan
COMMITTEE
Measure/Topic | Minimum Measure (in order of app) | Priority if Applicable | Activity - BMP | Responsbile Entity | Frequency | Evaluation Mechanism/Measure of Usage of Facilities or Material | Comments - activity | Complete
Maintain Master PEP | 2 |  | Maintain master PEP document. Update BMPs completed in preparation for progress report submittal. | PEP Committee | Indicate completed BMPs for progress report (1st and 4th year of permit cycle)
Set PEP Priorities | 2 |  | Set priorities based on survey results, cost effectiveness, etc. | PEP Committee | As Needed | Use survey results and other described evaluations of effectiveness to set priorities
PEP Evaluation and Effectiveness | 2 |  | Provide information to GLRC members on an updated survey to evaluate the effectiveness of the PEP. | PEP Committee | Once per permit cycle. (following permit) | Recently completed, will do again with follow up evaluation in 2023
PEP Evaluation and Effectiveness | 2 |  | Coordinate a follow up survey to evaluate and determine effectiveness of the PEP. | PEP Committee | Once per permit cycle. (following permit) | Survey results will be used to guide further implementation activities. | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | M | Periodically review news articles to ensure they are flexible with different media outlets and are accurate. Update as appropriate. | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for news article review at least once a permit cycle.
PEP C: Reporting Illicit Discharges | 2 | H | Periodically review illicit discharge education strategy and guide updates as appropriate. | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for IDEP outreach strategy review at least once a permit cycle. | Corresponding topic areas: A, B, F, G
PEP D: Car Washing | 2 | M | Periodically review poster/brochure series content on: car washing, motor oil, fertilizer, pet waste, and guide updates as appropriate. | PEP Committee | Review at least once per permit cycle | PEP meeting assembled for educational material review at least once a permit cycle. | Corresponding topic area: A
PEP F: Disposal of Pet Waste, etc. | 2 | M | Periodically review materials and strategies related to leaf litter diposal and grass clipping outreach. Guide updates as appropriate | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for educational material review at least once a permit cycle. | Corresponding topic area: A
PEP I: GI & LID | 2 | H | Periodically review and guide updates of LID/GSI outreach materials (brochures, digital strategy, etc) | PEP Committee | Review at least once per permit cycle | PEP meeting assembled to review LID/GSI materials at least once per permit cycle.
PEP I: GI & LID | 2 | H | Develop programming for educational seminars/events to encourage GSI and GSI best management practices. | PEP Committee | 2 per permit cycle | Number of events | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | M | Explore opportunities to connect with local business regarding pollution prevention through stormwater runoff. This may include business publications, presentation to associations, focus groups, etc. | PEP Committee | Twice per permit cycle | Number of businesses reached, etc.
IDEP - collaboration | 3 |  | Meet once a year to discuss member issues related to implementation and management of IDEP, sharing concerns, situation, solutions, etc. | IDEP Committee | Annually | Number of participants
PCSWC - collaboration | 5 | 1 | Maintain template ordinance; design manual (including inspection checklists, etc.); and policy and procedures manual for post-construction stormwater control measures as developed by GLRC members. | Ord/BMP Com (Technical workgroup | Continuously
PCSWC - collaboration | 5 | 2 | Convene the Post-Construction Stormwater Control Technical Workgroup to discuss implementation strategies, etc. | Ord/BMP Com (Technical workgroup | Annually | Number of participants that have successfully implemented the program
PCSWC - collaboration & education | 5 | 3 | Develop a series of LID presentations that are beneficial to GLRC members (street trees, stormceptors, local project details, etc.) | Ord/BMP Com | 5 per permit cycle | Number of participants
P2 Good Housekeeping | 6 | 1 | Maintain the GLRC developed "Pollution Prevention and Good Housekeeping for Municipal Activities" handbook. | Ord/BMP Com | Continuously
P2 Good Housekeeping | 6 | 2 | Update the handbook as necessary (current version can be used to meet requirements). | Ord/BMP Com | Continuously

## Brochures D
Hand Out Descriptor | These are materials that satisfy the requirement in required PEP Topic Area D
NEW Responsible Car Washing Trifold Brochure
New Pet Waste Management Trifold Brochure
New Motor Oil Management Trifold brochure
New Lawn and Garden Trifold Brochure
New Green Infrastructure trifold Brochures
New WATERSHED INFO brochure
PIP Responsible Car Washing tri-fold
PIP Pet Waste Management tri-fold
3x7” PIP turtle/ink card | DOUBLE CLICK
3x7” PIP swimmer/ink card | For Reference Images
3x7” PIP Fish/ink card
5x5” PIP Pick Up Pet Waste card
5x5” PIP “Pour Sparingly” card
5x5” PIP frog/ink card
Motor Oil” tri-fold (older)
Lawn and Garden tri-fold (older)
“Car Wash” trifold (older)
“Pet Waste” tri-fold (older)
“Do You Know Your Watershed Trifold
“Keep your lawn green and water clean” trifold
PIP Pet Waste Poster
Pet Waste Poster (older)
Car Washing Poster (older)
Motor Oil Poster (older)
Fertilizer Poster (older)
Dog Waste Bag Dispensers

## Brochures F
Hand Out Descriptor
These are materials that satisfy the requirement in required PEP Topic Area F
New WATERSHED INFO Brochure
New Green Infrastructure Trifold Brochure
New Lawn and Garden Trifold Brochure
Rain Garden Seed Cards | DOUBLE CLICK
3x7” PIP swimmer/ink card | For Reference Images
5x5” PIP “Pour Sparingly” turtle ink card
3x7 PIP Turtle Learn what you can do
3x7 PIP Fish Learn what you can do
Lawn and Garden tri-fold (older)
“Do You Know Your Watershed Trifold
“Keep your lawn green and water clean” trifold
Fertilizer Poster (older)
Garden Designs for Homeowners
Bracelets

## PEP_ Complete List Action Plan
Measure/Topic | Minimum Measure (in order of app) | Action Number | Priority if Applicable | Activity - BMP | Responsbile Entity | Frequency | Evaluation Mechanism/Measure of Usage of Facilities or Material | Comments - activity | Complete
Public Participation | 1 | 1 |  | Post master PEP, Progress Report template, etc. to the GLRC website. | GLRC Crd | Continuously | Track website traffic related to the documents
Public Participation | 1 | 2 |  | Post SWMP and Progress Reports to the community website. Include a link on the community website to the GLRC website. Follow the local public notice requirements. | Permittees | Continously. Update SWMP and Progress Report links to keep current. | Track website traffic
Maintain Master PEP | 2 | 1 |  | Maintain master PEP document. Update BMPs completed in preparation for progress report submittal. | PEP Committee | Indicate completed BMPs for progress report (1st and 4th year of permit cycle)
Develop and Maintain Master PEP | 2 | 2 |  | Update the PEP based on BMPs completed as part of community specific programs and procedures. | Permittees | Update BMPs completed with progress report. 1st and 4th year of permit.
Set PEP Priorities | 2 | 3 |  | Set priorities based on survey results, cost effectiveness, etc. | PEP Committee | As Needed | Use survey results and other described evaluations of effectiveness to set priorities
PEP Evaluation and Effectiveness | 2 | 4 |  | Provide information to GLRC members on an updated survey to evaluate the effectiveness of the PEP. | PEP Committee | Once per permit cycle. (following permit) | Recently completed, will do again with follow up evaluation in 2023
PEP Evaluation and Effectiveness | 2 | 5 |  | Coordinate a follow up survey to evaluate and determine effectiveness of the PEP. | PEP Committee | Once per permit cycle. (following permit) | Survey results will be used to guide further implementation activities.
PEP Evaluation and Effectiveness | 2 | 6 |  | Partner with the GLRC to conduct another follow up survey to determine PEP effectiveness . | Permittees | Once per permit cycle | Survey completed at end of permit cycle.
PEP: Website Management and Education | 2 | 7 |  | Update the www.mywatersheds.org website and social media outlets with watershed wide educational material, permit information and meeting information for the various committees of the GLRC. Include links to all community websites. | GLRC Crd | Continuously | Website traffic, social media analytics
PEP Collaboration | 2 | 8 |  | Continue to represent the GLRC on a regional public education campaigns with the Middle Grand River Organization of Watersheds (MGROW). | GLRC Crd | Continuously | Effectiveness of educational materials/strategies provided by MGROW | .
PEP A: Public Responsibility & Watershed Stewardship | 2 | 9 | M | Continue to maintain watershed signage. | Permittees | Replace as needed | Number of signs, maintenance activities.
PEP A: Public Responsibility & Watershed Stewardship | 2 | 10 | M | Promote "do you know your watershed" brochure, or related materials to general watershed education through website, social media, etc., update as appropriate. | GLRC Crd | Update as needed. Materials will be distributed at events, annually at Adopt A River, QWS, MWEA Watershed Summit, etc. | Number of brochures/materials provided to the public. Web traffic and social media analytics. | Corresponding topic area: B
PEP A: Public Responsibility & Watershed Stewardship | 2 | 11 | M | Promote "do you know your watershed" brochure, or related materials to general watershed education through events, lobby, and website | Permittees | Continously in lobby. during events | Number of brochures/materials provided to the public, web site traffic | Corresponding topic area: B
PEP A: Public Responsibility & Watershed Stewardship | 2 | 12 | M | Promote Mid-MEAC's volunteer stream monitoring effort through website and social media | GLRC Crd | Fall and Spring of Each Year (if event is held) | Potential volunteers reached through website and social media | Corresponding topic areas: C, J
PEP A: Public Responsibility & Watershed Stewardship | 2 | 13 |  | Display GLRC educational display at annual events (ex. Adopt A River/Quiet water,etc) | GLRC Crd | Annual events | Number of events the display is used for | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | 14 | M | Display GLRC educational display in lobby and/or community events. | Permittees | Displayed in lobby or public location at least once annually for 2-3 weeks | Used at least once a year by each permittee. | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | 15 | M | Periodically review news articles to ensure they are flexible with different media outlets and are accurate. Update as appropriate. | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for news article review at least once a permit cycle. | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | 16 | M | Promote and distribute news article series developed for PEP topic areas on website/local newsletters/community news papers (as indicated in PEP) | Permittees | Continuously available online. Distribute in community newsletter if committed, as frequently as committed in PEP | Number of articles distributed, track website traffic | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | 17 | M | Promote and distribute news article series developed for PEP topic areas through email distribution, website, and social media | GLRC Crd | Monthly social media post of article or related content. Continously on website. with quarterly newsletter | Number of articles on website, email distribution, web traffic, social media analytics | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP B: MS4 Connection | 2 | 18 | H | Maintain and update the GLRC webpage. Sections "Stormwater Basics" and "What's a Watershed?" promote watershed health information and steps citizens can take. Update as appropriate. | GLRC Crd | Continuously | Track website traffic on page, social media analytics | Corresponding topic area: A
PEP B: MS4 Connection | 2 | 19 | H | Quarterly newsletters and annual report developed & distributed through email list, social media and website. | GLRC Crd | Quarterly/Annually | Number of people reached via email, track website traffic, social media | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP B: MS4 Connection | 2 | 20 | H | Distribute quarterly newsletter and annual report to public via community website, lobbies, and provide to administration. | Permittees | Quarterly/Annually | Number of people reached, track website traffic, copies distributed | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP C: Reporting Illicit Discharges | 2 | 21 | H | Maintain the GLRC webpage, social media that lists contact information for all members and the state hotline regarding reporting of illicit discharges and illegal dumping. | GLRC Crd | Continuously | Track website traffic on IDEP section. |  | Y
PEP C: Reporting Illicit Discharges | 2 | 22 | H | Periodically review illicit discharge education strategy and guide updates as appropriate. | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for IDEP outreach strategy review at least once a permit cycle.
PEP C: Reporting Illicit Discharges | 2 | 23 | H | Provide contact information for reporting illicit discharges and illegal dumping on website. | Permittees | Continuously | Website traffic
PEP D: Car Washing | 2 | 24 | M | Periodically review poster/brochure series content on: car washing, motor oil, fertilizer, pet waste, and guide updates as appropriate. | PEP Committee | Review At least once per permit cycle | PEP meeting assembled for educational material review at least once a permit cycle. | Corresponding topic areas: A, B, F, G
PEP D: Car Washing | 2 | 25 | M | Promote the poster/brochure series (or similar content) on: car washing, motor oil, fertilizer, pet waste. Provide at community events , website and lobbies | Permittees | Continuously | Track number of materials provided to public, website traffic, | Corresponding topic areas: A, B, F, G
PEP D: Car Washing | 2 | 26 | M | Promote the poster/brochure series (or similar content) on: car washing, motor oil, fertilizer, pet waste. Provide at community events and post to website and social media | GLRC Crd | Continuously | Track number of materials provided to public, website traffic, and social media analytics | Corresponding topic areas: A, B, F, G
PEP E: Disposal of Pesticides | 2 | 27 | M | Coordinate with Topic Area G
PEP F: Disposal of Pet Waste, etc. | 2 | 28 | M | Periodically review materials and strategies related to leaf litter diposal and grass clipping outreach. Guide updates as appropriate | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for educational material review at least once a permit cycle. | Corresponding topic area: A
PEP F: Disposal of Pet Waste, etc. | 2 | 29 | M | Post materials related to leaf litter disposal and grass clippings to website, provide at community events. | Permittees | Continuously | Track number of materials provided to the public, website traffic | Corresponding topic area: A
PEP F: Disposal of Pet Waste, etc. | 2 | 30 | M | Continue to maintain pet waste signage at local parks, dog parks, trails, etc. | Permittees | Continuously | Track number of signs posted, maintenance activities | Corresponding topic areas: A, D
PEP G: P2 HHW | 2 | 31 | M | Promote local household hazardous waste and recycling events via email and website postings, social media. | GLRC Crd | Continuously | Website traffic and social media analytics, newletters distribution. | Corresponding topic areas: D, E | Y
PEP G: P2 HHW | 2 | 32 | M | Promote local household hazardous waste, local travel trailer waste stations, yard waste procedures and recycling events via email and website postings | Permittees | Seasonally | Website Traffic | Corresponding topic areas: D, E
PEP H: Septic System Care | 2 | 33 | L | Coordinate with Topic Area A/Post links to local County programs related to septic inspections (Ingham County). Promote proper septic system care and 319 partner materials, etc. on GLRC website, social media. | GLRC Crd | Continuously | Website traffic, social media analytics | Corresponding topic area: A | Y
PEP H: Septic System Care | 2 | 34 | L | Coordinate with Topic Area A/Post links to local County programs related to septic inspections (Ingham Counties). Promote proper septic system care on website. | Permittees | Continuously | Website traffic | Corresponding topic area: A | Y
PEP I: GI & LID | 2 | 35 | H | Periodically review and guide updates of LID/GSI outreach materials (brochures, digital strategy, etc) | PEP Committee | Review at least once per permit cycle | PEP meeting assembled to review LID/GSI materials at least once per permit cycle. | Corresponding topic area: A
PEP I: GI & LID | 2 | 36 | H | Promote LID/GSI brochure, post on website, , lobby, etc. | Permittees | Continuously | Track number of materials provided to the public and website traffic | Corresponding topic area: A
PEP I: GI & LID | 2 | 37 | H | Promote LID/GSI brochure, post on website, social media, and use with educational display | GLRC Crd | Continuously | Track number of materials provided to the public, website traffic, social media analytics. | Corresponding topic area: A
PEP I: GI & LID | 2 | 38 | H | Maintain and update the GLRC webpage listing local LID projects. | GLRC Crd | Continuously | Track website traffic and number of projects posted. | Corresponding topic area: A
PEP I: GI & LID | 2 | 39 | H | Promote local projects on website, public meetings, etc. Share with GLRC Crd for inclusion on MyWatersheds.org | Permittees | Continously | Track website traffic, number of projects posted | Corresponding topic area: A
PEP I: GI & LID | 2 | 40 | H | Develop programming for educational seminars/events to encourage GSI and GSI best managmenet practices. | PEP Committee | 2 per permit cycle | Number of events
PEP I: GI & LID | 2 | 41 | H | Organize seminars/events that GSI and GSI best management practices. Promote through email, websites, social media. | GLRC Crd | 2 per permit cycle | Track number of participants and number of events | Corresponding topic area: A
PEP I: GI & LID | 2 | 42 | H | Send appropriate staff/elected officials to GLRC seminars. | Permittees | 2 per permit cycle | Track number of participants | Corresponding topic area: A
PEP I: GI & LID | 2 | 43 | H | Promote Greening Mid-Michigan on website | GLRC Crd | Continuously | Website traffic/video views | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | 44 | M | Explore opportunities to connect with local business regarding pollution prevention through stormwater runoff. This may include business publications, presentation to associations, focus groups, etc. | PEP Committee | Twice per permit cycle | Number of businesses reached, etc. | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | 45 | M | Educate business community on MS4 pollution prevention. Share information on how operations impact MS4 and how businesses can help educate costumers | PEP Committee | Outreach to the business sector twice during permit cycle. | Number of businesses reached, etc. | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | 46 | M | If you have an industrial pre-treatment program, describe your connection with local businesses, industries here. The IPTP can help you connect and ultimately educate them. | Permittees | Continuously | Number of business reached, etc. | Corresponding topic area: A
Progress Reports | 8 | 2 |  | Finalize and submit progress report | Permittees | 1st and 4th year of permit cycle
PEP Committee – Yellow
Individual Permittee Actions – White
GLRC Coordinator – Green
Not required to be in SWMP (should already be in place/done as a pre-application process)

## PEP_Permittee Action Plan
Associated Brochures and other hand-outs
Measure/Topic | Minimum Measure (in order of app) | Action Number | Priority if Applicable | Activity - BMP | Responsbile Entity (if committed to in PEP) | Frequency | Evaluation Mechanism/Measure of Usage of Facilities or Material | Comments - activity | Complete
Public Participation | 1 |  |  | Post SWMP and Progress Reports to the community website. Include a link on the community website to the GLRC website. Follow the local public notice requirements. | Permittees | Continously. Update SWMP and Progress Report links to keep current. | Track website traffic
Develop and Maintain Master PEP | 2 | 2 |  | Update the PEP based on BMPs completed as part of community specific programs and procedures. | Permittees | Update BMPs completed with progress report. 1st and 4th year of permit.
PEP Evaluation and Effectiveness | 2 | 6 |  | Partner with the GLRC to conduct another follow up survey to determine PEP effectiveness . | Permittees | Once per permit cycle | Survey completed at end of permit cycle.
PEP A: Public Responsibility & Watershed Stewardship | 2 | 9 | M | Continue to maintain watershed signage. | Permittees | Replace as needed | Number of signs, maintenance activities.
PEP A: Public Responsibility & Watershed Stewardship | 2 | 11 | M | Promote "do you know your watershed" brochure, or related materials to general watershed education through events, lobby, and website | Permittees | Continously in lobby. during events | Number of brochures/materials provided to the public, web site traffic | Corresponding topic area: B |  | "Do You Know Your Watershed" Tri-fold, bracelets, stickers, etc.
PEP A: Public Responsibility & Watershed Stewardship | 2 | 14 | M | Display GLRC educational display in lobby and/or community events. | Permittees | Displayed in lobby or public location at least once annually for 2-3 weeks | Display utilized annually | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | 16 | M | Promote and distribute news article series developed for PEP topic areas on website/local newsletters/community news papers (as indicated in PEP) | Permittees | Continuously available online. Distribute in community newsletter if committed, as frequently as committed in PEP | Number of articles distributed, track website traffic | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP B: MS4 Connection | 2 | 20 | H | Distribute quarterly newsletter and annual report to public via community website, lobbies, and provide to administration. | Permittees | Quarterly/Annually | Number of people reached, track website traffic, copies distributed | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP C: Reporting Illicit Discharges | 2 | 23 | H | Provide contact information for reporting illicit discharges and illegal dumping on website. | Permittees | Continuously | Website traffic
PEP D: Car Washing | 2 | 25 | M | Promote the poster/brochure series (or similar content) on: car washing, motor oil, fertilizer, pet waste. Provide at community events , website and lobbies | Permittees | Continously | Track number of materials provided to public, website traffic, | Corresponding topic areas: A, B, F, G |  | PEP D: Handouts
PEP E: Disposal of Pesticides | 2 | 27 | M | Coordinate with Topic Area G
PEP F: Disposal of Pet Waste, etc. | 2 | 29 | M | Post materials related to leaf litter disposal and grass clippings to website, provide at community events. | Permittees | Continuously | Track number of materials provided to the public, website traffic | Corresponding topic area: A |  | PEP F: Handouts
PEP F: Disposal of Pet Waste, etc. | 2 | 30 | M | Continue to maintain pet waste signage at local parks, dog parks, trails, etc. | Permittees | Continuously | Track number of signs posted, maintenance activities | Corresponding topic areas: A, D
PEP G: P2 HHW | 2 | 32 | M | Promote local household hazardous waste, local travel trailer waste stations, yard waste procedures and recycling events via email and website postings | Permittees | Seasonally | Website Traffic | Corresponding topic areas: D, E
PEP H: Septic System Care | 2 | 34 | L | Coordinate with Topic Area A/Post links to local County programs related to septic inspections (Ingham Counties). Promote proper septic system care on website. | Permittees | Continuously | Website traffic | Corresponding topic area: A
PEP I: GI & LID | 2 | 36 | H | Promote LID/GSI brochure, post on website, , lobby, etc. | Permittees | Continuously | Track number of materials provided to the public and website traffic | Corresponding topic area: A |  | Green Infrastructure Trifold Brochure, Rain Garden Seed Card
PEP I: GI & LID | 2 | 39 | H | Promote local projects on website, public meetings, etc. Share with GLRC Crd for inclusion on MyWatersheds.org | Permittees | Continuously | Track website traffic, number of projects posted | Corresponding topic area: A
PEP I: GI & LID | 2 | 42 | H | Send appropriate staff/elected officials to GLRC seminars. | Permittees | 2 per permit cycle | Track number of participants | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | 46 | M | If you have an industrial pre-treatment program, describe your connection with local businesses, industries here. The IPTP can help you connect and ultimately educate them. | Permittees |  | Number of business reached, etc. | Corresponding topic area: A
Progress Reports | 8 | 2 |  | Finalize and submit progress report | Permittees | 1st and 4th year of permit cycle
Individual Permittee Actions – White

## PEP_Committee Action Plan
Measure/Topic | Minimum Measure (in order of app) | Action Number | Priority if Applicable | Activity - BMP | Responsbile Entity | Frequency | Evaluation Mechanism/Measure of Usage of Facilities or Material | Comments - activity | Complete
Maintain Master PEP | 2 | 1 |  | Maintain master PEP document. Update BMPs completed in preparation for progress report submittal. | PEP Committee | Indicate completed BMPs for progress report (1st and 4th year of permit cycle)
Set PEP Priorities | 2 | 2 |  | Set priorities based on survey results, cost effectiveness, etc. | PEP Committee | As Needed | Use survey results and other described evaluations of effectiveness to set priorities
PEP Evaluation and Effectiveness | 2 | 4 |  | Provide information to GLRC members on an updated survey to evaluate the effectiveness of the PEP. | PEP Committee | Once per permit cycle. (following permit) | Recently completed, will do again with follow up evaluation in 2023
PEP Evaluation and Effectiveness | 2 | 5 |  | Coordinate a follow up survey to evaluate and determine effectiveness of the PEP. | PEP Committee | Once per permit cycle. (following permit) | Survey results will be used to guide further implementation activities. | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | 15 | M | Periodically review news articles to ensure they are flexible with different media outlets and are accurate. Update as appropriate. | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for news article review at least once a permit cycle.
PEP C: Reporting Illicit Discharges | 2 | 22 | H | Periodically review illicit discharge education strategy and guide updates as appropriate. | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for IDEP outreach strategy review at least once a permit cycle. | Corresponding topic areas: A, B, F, G
PEP D: Car Washing | 2 | 24 | M | Periodically review poster/brochure series content on: car washing, motor oil, fertilizer, pet waste, and guide updates as appropriate. | PEP Committee | Review at least once per permit cycle | PEP meeting assembled for educational material review at least once a permit cycle. | Corresponding topic area: A
PEP F: Disposal of Pet Waste, etc. | 2 | 28 | M | Periodically review materials and strategies related to leaf litter diposal and grass clipping outreach. Guide updates as appropriate | PEP Committee | Review at least once per permit cycle | PEP Meeting assembled for educational material review at least once a permit cycle. | Corresponding topic area: A
PEP I: GI & LID | 2 | 35 | H | Periodically review and guide updates of LID/GSI outreach materials (brochures, digital strategy, etc) | PEP Committee | Review at least once per permit cycle | PEP meeting assembled to review LID/GSI materials at least once per permit cycle.
PEP I: GI & LID | 2 | 40 | H | Develop programming for educational seminars/events to encourage GSI and GSI best management practices. | PEP Committee | 2 per permit cycle | Number of events | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | 44 | M | Explore opportunities to connect with local business regarding pollution prevention through stormwater runoff. This may include business publications, presentation to associations, focus groups, etc. | PEP Committee | Twice per permit cycle | Number of businesses reached, etc.
PEP Committee – Yellow
Not required to be in SWMP (should already be in place/done as a pre-application process)

## PEP_Coordinator Action Plan
Measure/Topic | Minimum Measure (in order of app) | Action Number | Priority if Applicable | Activity - BMP | Responsbile Entity | Frequency | Evaluation Mechanism/Measure of Usage of Facilities or Material | Comments - activity | Complete
Public Participation | 1 | 1 |  | Post master PEP, Progress Report template, etc. to the GLRC website. | GLRC Crd | Continuously | Track website traffic related to the documents
PEP: Website Management and Education | 2 | 7 |  | Update the www.mywatersheds.org website and social media outlets with watershed wide educational material, permit information and meeting information for the various committees of the GLRC. Include links to all community websites. | GLRC Crd | Continuously | Website traffic, social media analytics
PEP Collaboration | 2 | 8 |  | Continue to represent the GLRC on a regional public education campaigns with the Middle Grand River Organization of Watersheds (MGROW). | GLRC Crd | Continuously | Effectiveness of educational materials/strategies provided by MGROW | .
PEP A: Public Responsibility & Watershed Stewardship | 2 | 10 | M | Promote "do you know your watershed" brochure, or related materials to general watershed education through website, social media, etc., update as appropriate. | GLRC Crd | Update as needed. Materials will be distributed at events, annually at Adopt A River, QWS, MWEA Watershed Summit, etc. | Number of brochures/materials provided to the public. Web traffic and social media analytics. | Corresponding topic area: B
PEP A: Public Responsibility & Watershed Stewardship | 2 | 12 | M | Promote Mid-MEAC's volunteer stream monitoring effort through website and social media | GLRC Crd | Fall and Spring of Each Year (if event is held) | Potential volunteers reached through website and social media | Corresponding topic areas: C, J
PEP A: Public Responsibility & Watershed Stewardship | 2 | 13 |  | Display GLRC educational display at annual events (ex. Adopt A River/Quiet water,etc) | GLRC Crd | Multiple times annually | Number of events the display is used for | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP A: Public Responsibility & Watershed Stewardship | 2 | 17 | M | Promote and distribute news article series developed for PEP topic areas through email distribution, website, and social media | GLRC Crd | Monthly social media post of article or related content. Continously on website. with quarterly newsletter | Number of articles on website, email distribution, web traffic, social media analytics | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP B: MS4 Connection | 2 | 18 | H | Maintain and update the GLRC webpage. Sections "Stormwater Basics" and "What's a Watershed?" promote watershed health information and steps citizens can take. Update as appropriate. | GLRC Crd | Continuously | Track website traffic on page, social media analytics | Corresponding topic area: A
PEP B: MS4 Connection | 2 | 19 | H | Quarterly newsletters and annual report developed & distributed through email list, social media and website. | GLRC Crd | Quarterly/Annually | Number of people reached via email, track website traffic, social media | Corresponding topic areas: B, C, D, E, F, G, H, I, J, K
PEP C: Reporting Illicit Discharges | 2 | 21 | H | Maintain the GLRC webpage, social media that lists contact information for all members and the state hotline regarding reporting of illicit discharges and illegal dumping. | GLRC Crd | Continuously | Track website traffic on IDEP section. |  | Y
PEP D: Car Washing | 2 | 26 | M | Promote the poster/brochure series (or similar content) on: car washing, motor oil, fertilizer, pet waste. Provide at community events and post to website and social media | GLRC Crd | Continuously | Track number of materials provided to public, website traffic, and social media analytics | Corresponding topic areas: A, B, F, G
PEP G: P2 HHW | 2 | 31 | M | Promote local household hazardous waste and recycling events via email and website postings, social media. | GLRC Crd | Continuously | Website traffic and social media analytics, newletters distribution. | Corresponding topic areas: D, E | Y
PEP H: Septic System Care | 2 | 33 | L | Coordinate with Topic Area A/Post links to local County programs related to septic inspections (Ingham County). Promote proper septic system care and 319 partner materials, etc. on GLRC website, social media. | GLRC Crd | Continuously | Website traffic, social media analytics | Corresponding topic area: A | Y
PEP I: GI & LID | 2 | 37 | H | Promote LID/GSI brochure, post on website, social media, and use with educational display | GLRC Crd | Continuously | Track number of materials provided to the public, website traffic, social media analytics. | Corresponding topic area: A
PEP I: GI & LID | 2 | 38 | H | Maintain and update the GLRC webpage listing local LID projects. | GLRC Crd | Continuously | Track website traffic and number of projects posted. | Corresponding topic area: A
PEP I: GI & LID | 2 | 41 | H | Organize seminars/events that GSI and GSI best management practices. Promote through email, websites, social media. | GLRC Crd | 2 per permit cycle | Track number of participants and number of events | Corresponding topic area: A
PEP I: GI & LID | 2 | 43 | H | Promote Greening Mid-Michigan on website | GLRC Crd | Continuously | Website traffic/video views | Corresponding topic area: A
PEP K: Business/Commercial education | 2 | 45 | M | Educate business community on MS4 pollution prevention. Share information on how operations impact MS4 and how businesses can help educate costumers | PEP Committee | Twice per permit cycle | Number of businesses reached, etc. | Corresponding topic area: A
GLRC Coordinator – Green